## Asset Sheet
Create a Wedding Budget in this worksheet. Enter details in tables in Expenses worksheet to update the summary and chart in the current worksheet. Helpful instructions on how to use this worksheet are in cells in this column. Wedding Date label is in cell B3.
Budget Summary Table starting in cell B5 is auto updated. Next instruction is in cell A18. | Asset | ESTIMATED | ACTUAL | Due | Priority | Hours | Refrence
| Grenade | 3 Days | 1 Day |  | B | 6 Hours | https://www.gettyimages.ca/photos/hand-grenade?mediatype=photography&phrase=hand%20grenade&sort=mostpopular
| Computer | 1 Day | 2 Days |  | B | 6 Hours | https://www.dell.com/en-us/shop/cty/pdp/spd/xps-8930-se-desktop
| UI Mock Up | 3 Days |  | May 13th | A | 4 hours | https://gameui.tumblr.com/page/2
| Water Shader x 2 | 2 days |  | May 15th | A | (1 complete *1 hour) | https://blenderartists.org/t/realistic-water-shader-cycles-volumes/646348
| Force Field Shader | 2 Days |  | May 15th | C | 2 hours | http://2.bp.blogspot.com/-fhbYEcgVclk/VJ0qfP6BzTI/AAAAAAAAAJ4/e18mSREjwUQ/s1600/Star%2BWars%2B-%2BD6%2B-%2BEquipment%2BStats%2BNetbook_img_109.jpg
| Dump Truck | 7 Days |  | May 15th | B | Backlogging for now | https://www.turbosquid.com/3d-models/big-dump-truck-model-1432150
| Grass Prefab | 3 Days |  | May 22nd | A | back Logged | https://forum.unity.com/threads/shading-a-terrain-tree-prefab-to-match-the-way-detail-meshes-are-rendered.730847/
| Grass Shader | 2 Days |  | May 22nd | B | back logged | https://halisavakis.com/my-take-on-shaders-grass-shader-part-ii/
| Cattle Prod | 4 Days |  | June 3rd | A | currently doing | https://deadrising.fandom.com/wiki/Electric_Prod_(Dead_Rising_2)
| Moon Beam Shader | 3 Days |  | May 29th | A | (not working, need to redo) | https://www.picuki.com/media/2249558051178031250
Pie chart in cell B18 is auto updated. | Moon Beam PreFab | 4 Days |  | May 29th | A |  | a pile of planes together
| Explosion Particle Effect | 3 Days |  | June 19th | A |  | https://www.gamedev.net/articles/visual-arts/make-a-particle-explosion-effect-r2701/
| Electric Particle Effect | 3 Days |  | June 19th | A | 1 hour* needs texture | https://stylizedstation.com/tutorials/quick-tutorial-creating-electricity-effects-in-unity3d/
| Howl Particle Effect | 3 Days |  | June 19th | A |  | https://www.youtube.com/watch?v=MvHuD09Sr7I
| Wolf Sense Shader | 5 Days |  | June 26th | B |  | https://gfycat.com/peskymarvelousammonite
| Extra ModKit Pieces | 1 Week |  | June 26th | C |  | dependent on what others make
Asset List
Hour and a half Min Per Day
Fully Complete In Game Ready